# ClonalGE Revision — Coding Task Division

This document divides the coding tasks from the reviewer response between two people. Text/manuscript changes are handled separately.

# All Coding Tasks (from Revision TODOs)

| ID | Task | Effort |
| --- | --- | --- |
| T2 | Implement Tumoroscope + NB regression comparison | Medium |
| T3 | Multi-chain agreement analysis (run chains, compute correlations) | Medium-High |
| T4 | Hyperparameter sensitivity analysis (perturb params, re-run model) | Medium-High |
| T5 | Bayesian DGE: posterior probability from MCMC samples | Medium |
| T6 | GSEA + COSMIC validation | Medium |
| T7 | Reference-free deconvolution comparison (Tangram/STdeconvolve) | Medium |
| T8 | Assumption-violating simulation (zero-inflated NB, batch effects) | Medium |
| T9 | Runtime & scalability benchmarking | Medium |
| T10 | Supplementary variable/parameter table | Low |
| T11 | Mutation count reporting (run pipeline, count at each step) | Low |

# Person 1: Model Comparisons & Benchmarking

Theme: This person runs external tools and benchmarks against ClonalGE. They do not modify ClonalGE internals — they write new scripts around it.

| ID | Task | What to do |
| --- | --- | --- |
| T2 | Tumoroscope + NB regression | Implement NB GLM (scipy/statsmodels) as post-processing after Tumoroscope. Run on 3 simulation setups + prostate data. Produce results for Figures 2 & 5. |
| T7 | Tangram/STdeconvolve comparison | Apply a reference-free deconvolution tool to simulated data, treating clones as cell types. Compare inferred B and H against ground truth. |
| T8 | Assumption-violating simulation | Design new simulation with zero-inflated NB and/or batch effects. Run ClonalGE on it, report performance degradation. |
| T9 | Runtime & scalability | Time the model varying S={100,300,600}, G={25,50,100,500}, I={100,200,400}. Create supplementary table/figure. Report hardware specs. |

# Person 2: Internal Analysis & Post-processing

Theme: This person works with ClonalGE output — MCMC samples, chain results, posterior distributions. T5 feeds directly into T6, so keeping them together avoids handoffs.

| ID | Task | What to do |
| --- | --- | --- |
| T5 | Bayesian DGE | From post-burn-in MCMC samples, compute P(B_k1,g > B_k2,g) for each gene and clone pair. Replace Wilcoxon results. Update Figure 3b. |
| T3 | Multi-chain agreement | Run 5-10 independent chains on prostate/simulated data. Compute pairwise Pearson correlations of H and B across chains. Create supplementary figure. |
| T4 | Hyperparameter sensitivity | Perturb alpha_g, beta, p_g by +/-25% and +/-50%. Re-run ClonalGE, report changes in inferred B and H. |
| T6 | GSEA + COSMIC | Use posterior probabilities from T5 to rank genes per clone. Run GSEA (gseapy) with MSigDB Hallmarks/KEGG. Check overlap with COSMIC prostate gene census. |

# Shared / Low Effort (assign to whoever finishes first)

| ID | Task |
| --- | --- |
| T10 | Supplementary variable/parameter table |
| T11 | Count mutations at each filtering step |
| T12 | Check emails for saved MCMC chains (before Person 2 re-runs chains for T3) |

# Dependencies

T12 should happen first — if old chains exist, Person 2 can skip re-running for T3/T5.

T5 must finish before T6 — GSEA needs the posterior probabilities.

Everything else is independent and can run in parallel.

# Why This Split Works

Zero overlap: Person 1 writes new comparison scripts. Person 2 works with existing ClonalGE output.

Zero blocking: Neither person waits on the other (except the shared T12 check).

Both are pure coding tasks: No manuscript editing required from either person.